## Sheet1
Sprint No. | Date | Event | Group members in attendance | Description
1 | 2/2/22 | Meeting with client | jrw40, cw467, as1264, mf314 | Scrum master for this sprint: JRW40. Met with the client to clarify details about the product and to choose the initial user stories that they wanted.
scrum master: jrw40 | 2/3/22
| 2/4/22 | Weekly group meeting | zna2, jrw40, cw467, mf314 | Members agreed which user stories they would like to do and we assigned ourselves accordingly.
2/5/22
2/6/22
2/7/22
2/8/22
| 2/9/22 | Standup meeting | zna2, jrw40, cw467 | Took part in a standup meeting. The product was progressing well and details were agreed with members.
2/10/22
| 2/11/22 | Weekly group meeting, sprint standup | zna2, jrw40, cw467, mf314 | Met up with the group to update how the user stories are getting along and those group members that were assigned to the same user stories could help each other. Discussed what was going well with the sprint and what wasn't. We decided that calling each other on teams was the best way to help each other fix problems.
2/12/22
2/13/22
2/14/22
| 2/15/22 | Finalised code and recorded demonstration for customer | jrw40, cw467 | Finished coding and removing bugs. Went through the Issue board for sprint 1 and checked each definition of done ready to show the client. Recorded the demo for the client on 08/02/2022.
2 | 2/16/22 | Meeting with client | jrw40, cw467, as1264, mf314, zna2 | Scrum master for the sprint: CW467. Talked over our implementation with client, received great feedback. Client outlined the work for the next sprint and gave us sample questions a module convenor might ask
scrum master: cw467 | 2/17/22
| 2/18/22 | Weekly group meeting | jrw40, cw467, mf314, zna2 | Held a sprint review, discussed what worked well last sprint and outlined what we would do this sprint. Agreed that communicating more would benefit our team so that we are all aware of what each other are working on. Also discussed attendance at group meetings. Each member who attened assigned themselves to a user story to start working on
2/19/22
2/20/22
2/21/22
2/22/22
| 2/23/22 | Sprint Standup | zna2, jrw40, cw467 | Held a sprint standup, each wen't round and discuussed their progress on current user stories and what to work on next. We managed to finish the module grouping user story today. We also discussed the plan for finishing the module question form user story
2/24/22
| 2/25/22 | Weekly group meeting | zna2, jrw40, cw467 | Held another standup and discussed progress of module question user story and if anyone needed any help. We decieded to allocate ourselves to a particular problem within the user story to try and speed up the progress
2/26/22
2/27/22
2/28/22
3/1/22
3 | 3/2/22 | Meeting with client | zna2, jrw40, cw467 | Scrum master for the sprint: zna2. Talked over our implementation with client, received feedback and client wanted us to make two improvements on our second sprint and update the readme file with the installation instructions. The user stories will be worked on are chosen.
scrum master: zna2 | 3/3/22
| 3/4/22 | Weekly group meeting | zna2, jrw40, cw467, mf314 | We decided to work on a single user story at a time to speed up the process and assigned ourselves to a user story.
3/5/22
3/6/22
3/7/22
3/8/22
| 3/9/22 | Sprint Standup | zna2, jrw40, cw467 | Talked over our progress on user story and decide what to implement next.
3/10/22
| 3/11/22 | Weekly group meeting | jrw40, cw467, mf314 | Continued to work on the student question form submission, the test script for the preference set form and the creation of the test script for the add module form.
3/12/22
3/13/22
3/14/22
3/15/22
4 | 3/16/22 | Meeting with client | mf314, cw467, jrw40, zna2, as1264 | Scrum master for this sprint: mf314. Met with client and discussed how to further improve our implementation. Gave us good feedback, accepted 2 features and outlined what changes needed to be made going forwards. Now looking to work on allocating question set to students, specifying group sizes and getting students to fill answers in.
scrum master: mf314 | 3/17/22
| 3/18/22 | Weekly group meeting | mf314, cw467, jrw40, zna2 | Started to individually work on user stories after discussing what needed to be worked on following client meeting 2 days ago.
3/19/22
3/20/22
3/21/22
3/22/22
| 3/23/22 | Sprint Standup | mf314, cw467, jrw40, zna2 | Discussed our progress on the user stories we were individually working on. Gave feedback to each other and discussed what to implement next.
3/24/22
| 3/25/22 | Weekly group meeting | mf314, cw467, jrw40, zna2 | Discussed our implementations and what we needed to do to finish off our project. Set group deadline for task completion.
3/26/22
3/27/22
3/28/22
3/29/22